## Sprint-1
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete | Interviewing the Client | MD. Sifat Bin Islam | Delivered | 2-3 hours | 1.5 hours
Incomplete
Partially Complete
Complete | Collecting the Requirements from the interview | Md. Arifur Rahman Shihab | Delivered | 4-5 hours | 2 hours
Incomplete
Partially Complete
Complete | Reviewing the Requirements | Md. Sabbir Ahmed | Delivered | 2-3 hours | 2 hours
Incomplete
Partially Complete
Complete | Preparing questionnaire for the survey | Adnan Anan Sikder | Delivered | 4-5 hours | 4 hours
Incomplete
Partially Complete
|  |  |  | Summary of hours: | name 1
name 2
name 3
name 4
name 5

## Sprint-2
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete |  |  | connecting the backend with database | 1 hour | 1 hour
Incomplete |  |  | survey from 2 bank | 3 hours |  |  |  |  | Survey is postpond for now due to the national election.
Partially Complete | Taking Survey and build the backend for login and authentication | MD. Sifat Bin Islam | build the logic for login | 2 hours | 2 hours
Complete |  |  | surveying 2 bank | 3 hours
Incomplete |  |  | maintaining user table | 3 hours | 3 hours
Partially Complete | Taking Survey and build the backend for login and authentication | Md. Arifur Rahman Shihab | build logic for creating new account | 1 hour | 2 hours
Complete |  |  | manually test the system after completing the login feature | 2 hours | 3 hours
Incomplete |  |  | surveying 2 bank | 3 hours
Partially Complete | Taking Survey and helping with the frontend and testing the system | Md. Sabbir Ahmed | build login page for user | 2 hours | 2.5 hours
Complete |  |  | build the home page for the users | 3 hours | 3.5 hours
Incomplete |  |  | surveying 2 bank | 3 hours
Partially Complete | Taking Survey and Building the frontend for login page and home page | Adnan Anan Sikder | connecting the frontend with backend logic so that the user login from the frontend directly reflect on the database | 2 hours | 4 hours
|  |  |  | Summary of hours: | Sifat | 3 hours
[5 empty] | Shihab | 5 hours
[5 empty] | Sabbir | 5.5 hours
[5 empty] | Adnan | 7.5 hours

## Sprint-3
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete | Implementing Transaction Fundamentals (CRUD operations for transactions) | MD. Sifat Bin Islam | Build the api to manually add,view,edit and delete a transaction. | 3 hours | 4 hours
Incomplete |  |  | Connect the api to the Database | 2 hours | 1 hours
Partially Complete
Complete | Handling Image uploading to the site | Md. Arifur Rahman Shihab | Create Api Endpoint that accepts an image file | 4 hours | 3 hours
Incomplete |  |  | Saving the image file to users account | 1 hours | 2 hours
Partially Complete
Complete | Creating Transactions Dashboard on the user end | Md. Sabbir Ahmed | Create small dashboard for users to write their transaction manually | 2 hours | 3 hours
Incomplete |  |  | Checking the database is updating accordinly or not | 3 hours | 2 hours
Partially Complete
Complete | Improving the user interface and Creating a box for uploading Transaction image | Adnan Anan Sikder | Create a box in the user interface so that user can upload their transaction image | 2 hours | 1 hours
Incomplete |  |  | Making the user interface from skeleton form to a modern looking site | 4 hours | 4 hours
Partially Complete
|  |  |  | Summary of hours: | Sifat | 5 hours
[5 empty] | Shihab | 5 hours
[5 empty] | Sabbir | 5 hours
[5 empty] | Adnan | 6 hours

## Sprint-4
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete |  |  | user will login to the system via his/her gmail | 2 hours | 2 hours |  |  |  | meeting link with client
Incomplete |  | MD. Sifat Bin Islam | shift the entire codebase from fastapi to firebase as per client demand | 5 hours | 2 hours | 3 hours |  |  | meeting with client sprint-4.mp4
Partially Complete | Changing the login system and shifting the entire codebase to firebase
Complete
Incomplete |  | Md. Arifur Rahman Shihab | integrating OCR model that can recognize both english and bangla language to our system and can also deal with handwritten paper. | 4 hours | 2hours | 2 hours |  | Sifat Bin Islam supported him in ocr integration
Partially Complete | Finding a OCR model and integrating it to the project |  | add budget limitation features with warning | 2 hours | 2hours
Complete | testing the system after each integration |  | testing the system after changing the codebase to firebase. | 3 hours | 2 hours | 1 hours
Incomplete |  | Md. Sabbir Ahmed | test the newer OCR model throughly checking it performance against different test cases. | 3 hours | 3 hours
Partially Complete
Complete | Change the dashboard's button, page and improve the overall look of the app |  | Change the dashboard's button color to the page viewing | 2 hours | 2hours
Incomplete |  | Adnan Anan Sikder | Improve the overall outlook of the system make things simple but attractive to the users in a way that he/she gets to know what we are offering through our application. | 4 hours | 4 hours
Partially Complete
|  |  |  | Summary of hours: | Sifat | 4 hours
[5 empty] | Shihab | 4 hours
[5 empty] | Sabbir | 5 hours
[5 empty] | Adnan | 6 hours

## Sprint-5
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete | Reviewing the last week work
Incomplete |  | MD. Sifat Bin Islam | reviewing the codebase as no changes has made due to ocr integration problem | 5 hours | 6 hours
Partially Complete
Complete | Doing the unfinished work of last week
Incomplete |  | Md. Arifur Rahman Shihab | integrating OCR model that can recognize both english and bangla language to our system and can also deal with handwritten paper. | 5 hours | 5 hours |  |  | Sifat Bin Islam helped him with ocr integration
Partially Complete
Complete | Checking the overall system performance
Incomplete |  | Md. Sabbir Ahmed | test the total system as one | 5 hours | 5 hours
Partially Complete
Complete | Designing the dashboard page
Incomplete |  | Adnan Anan Sikder | Design the entire dashboard page of multiple functionality | 5 hours | 5 hours
Partially Complete
|  |  |  | Summary of hours: | Sifat | 6 hours
[5 empty] | Shihab | 5 hours
[5 empty] | Sabbir | 5 hours
[5 empty] | Adnan | 5 hours

## Sprint-6
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete | Reviewing Previous Work
Incomplete |  | MD. Sifat Bin Islam | Reviewing overall System integration and codebase | 5 hours | 5 hours
Partially Complete
Complete | Reviewing Previous Code
Incomplete |  | Md. Arifur Rahman Shihab | Reviewing Backend Code | 5 hours | 5 hours |  |  | Sifat Bin Islam helped him with ocr integration
Partially Complete
Complete | Reviewing Previous Code
Incomplete |  | Md. Sabbir Ahmed | Reviewing Frontend Code | 5 hours | 5 hours
Partially Complete
Complete | Reviewing Previous Code
Incomplete |  | Adnan Anan Sikder | Reviewing Frontend Code | 5 hours | 5 hours
Partially Complete
|  |  |  | Summary of hours: | Sifat | 5 hours
[5 empty] | Shihab | 5 hours
[5 empty] | Sabbir | 5 hours
[5 empty] | Adnan | 5 hours

## Sprint-7
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete | Integrating New Ocr model
Incomplete |  | MD. Sifat Bin Islam | Add Google Vision as ocr model | 5 hours | 5 hours
Partially Complete
Complete | Add Missing Crud operations
Incomplete |  | Md. Arifur Rahman Shihab | Add Update options that were missing in the previous version | 5 hours | 5 hours
Partially Complete
Complete | Design Frontend pages
Incomplete |  | Md. Sabbir Ahmed | Designing Login Page And Landing page | 5 hours | 5 hours
Partially Complete
Complete | Make Dashboard more intuitive
Incomplete |  | Adnan Anan Sikder | Add new features like Add Goal in the Dashboard | 5 hours | 5 hours
Partially Complete
|  |  |  | Summary of hours: | Sifat | 5 hours
[5 empty] | Shihab | 5 hours
[5 empty] | Sabbir | 5 hours
[5 empty] | Adnan | 5 hours

## Sprint-8
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete | Integrate the total system
Incomplete |  | MD. Sifat Bin Islam | integrating the total system as one and taking note on where it can be improved. like checking the font that was used in the frontend etc. | 5 hours | 5 hours
Partially Complete
Complete | Add unit testing in the backend
Incomplete |  | Md. Arifur Rahman Shihab | Add unit testing for api routes | 5 hours | 5 hours
Partially Complete
Complete | Add unit testing in the backend and help to add unit testing in the frontend
Incomplete |  | Md. Sabbir Ahmed | Add unit testing for schemas and help adnan with frontend unit testing | 5 hours | 5 hours
Partially Complete
Complete | Add unit testing in the backend
Incomplete |  | Adnan Anan Sikder | Add unit testing app.test in the frontend and checking the overall frontend. | 5 hours | 5 hours
Partially Complete
|  |  |  | Summary of hours: | Sifat | 5 hours
[5 empty] | Shihab | 5 hours
[5 empty] | Sabbir | 5 hours
[5 empty] | Adnan | 5 hours